# Children’s Youth & Family Stream

# Project Board Terms of Reference

# 1. Purpose

# The Project Board provides governance and decision-making for the project, ensuring alignment with Programme objectives and successful delivery of project outcomes

# 2. Objectives

Ensure the project delivers agreed outputs and outcomes.

Provide direction and resolve escalated issues.

Monitor progress, risks, and dependencies.

Approve changes within delegated authority.

Escalation to Programme Board

# 3. Scope

The Project Board will oversee:

Project deliverables and milestones.

Dependencies with other projects and the Programme.

Project-level risks, issues, and benefits realisation.

Stakeholder engagement and communications.

4. Responsibilities

Decision-Making: Approve scope, budget, timelines, and changes within authority

Risk & Issue Management: Review and mitigate Project-level risks.

Performance Monitoring: Track progress against KPIs and milestones.

Resource Management: Ensure adequate resources and resolve conflicts.

Benefits Realisation: Monitor delivery of expected benefits post-implementation.

# 5. Membership

Chair: +Ruth

Members:

Director of Education (Dep Chair)

Diocesan Youth Officer

Diocesan Children & Families Officer

Head of Strategic Programmes

Member of Diocese: Luke Whiteman

Member of Diocese: Ed Stoker ???

Member of Diocese: Sarah Steel ???

In attendance:

Children & Youth Delivery Officer (Project Lead)

Programme Finance Officer

# 6. Meeting Structure

Frequency: Quarterly

Quorum: 50% of members

Agenda: Distributed at least 5 working days before meeting.

Minutes: Issued within 5 working days after meeting.

# 7. Reporting

Project Lead provides a consolidated status report.

Escalated issues and decisions documented in minutes.

Reports submitted to Programme Board.

# 8. Authority

Approve Project-level decisions.

Escalate unresolved issues to Programme Board

Halt or reprioritise projects if necessary.

# 9. Review

This Terms of Reference will be reviewed annually or when significant changes occur.